## Project Dashboard
[16 empty] | Planned Resourcing |  | Actual Resourcing
Customer ID | Customer Name | LoB | ESA ID | ESA Name | Project Name | Service Line | Value Stream | PM / POC Name | SDLC Phase | RAG Status | Agile Adoption | DevOps Adoption | Key Updates - Update # 1 - Update # 2 -…… | Remarks | Project Type (T&M / FB / Fixed Capacity) | ON | Off | ON | Off
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | AEM | PV |  | Anirban Naha/ Maheswari Manickam | Development/Maintenance/Support | Green | AEM track running in Agile for JH.com | Source control using SVN and continuous integration using teamcity for all applications in AEM | JH RewardsLife: Discussions in progress with client regarding the change of tags from inspiration to life stories. Saleshub & Bermuda support: Steady State for Manulife Bermuda, DTM analytics integration in progress for saleshub JhBusinessAnalyzer: Development and unit testing for questionaire ,solution and mapping component JH.com Working on aem 6.4 upgradation for JH.com JHINS New Business Case Status : Working on timeout issue in stage for REST services | 1.JHRewardsLife 2.Saleshub & Manulife Bermuda support 3.JhBusinessAnalyzer 4.JH.Com 5. JHINS New business case status These five developmnets are going on in AEM track | T&M |  |  | 4 | 7
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | WMD | PV |  | Anirban Naha/ Samiran Das | Development | Green | WMD track running in AVM mode. |  | 1. JH Annuities PPM Raymond James on DTCC Settlement release planned on 27th April, 2018. 2. JH Annuities MVP Release planned on 20th July, 2018. 3. Risk Assessement Tool development on change requests and set up document creation are in progress . 4. COIN Bot - Migration current deployed bot service to new Azure app service. 5. JHA Deployment Automation using Team City | Enhancement and support of JH web/mobile portals are part of this track | T&M |  |  | 0 | 3
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000127878 | JHAS Valuation System Transformation | VST | PV |  | Anirban Naha | Implementation/Release support | Green | NA |  | 1. Development for the addition of the net premium funds in the PALLM is in progress |  | T&M | 2 | 1 | 2 | 2
1200377 | John Hancock Life Insurance Company- USA | USI | 1000152166 | JH USI App Dev Flex Misc | Microfocus Azure Migration | PV |  | Anirban Naha | Development | Green | Running in Agile Mode |  | 1. Retrofitted the branch for April release for both FRLT and RLTF application. 2.Compiled COBOL components for CARE,RLTF,FRLT through Team City and promoted the .dll files to the lower regions of Azure server 3. Built and deployed non-dll components i.e. procedures, Control cards and JCLs through Team City in the lower regions of Azure server |  | T&M |  |  | 1 | 3
Note on S5: Discussion going on for one resource reduction after March

## DMR
Customer ID | Customer Name | LoB | ESA ID | ESA Name | Project Name | Service Line | PM / POC Name | Upcoming Delivery Milestone (Next 3 months) | Planned Date | Actual Date | Current % Completion | Status (Not Started, WIP, Done) | Readiness to meet the next milestone (RAG) | Remarks | Issue / Action | Issue / Action Owner | Status
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | AEM | PV | Anirban Naha/ Maheswari Manickam | 1.QA Deployment for jh.com april sprint #2 2.Stage Deployment for NBCS | 1.4/27/2018 2.4/26/2018 |  | 1. 100% 2. 30% | 1. Done | 1. GREEN 2. GREEN
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | WMD | PV | Anirban Naha/ Samiran Das | 1. JH Annuities PPM Raymond James on DTCC Settlement (April '18 release) 2. JH Annuities MVP Implementation 3. Risk Asessment Tool development & set up document creation 4. COIN Bot migration to Azure 5. JHA Deployment Automation using Team City | 1. 4/27/2018 2. 7/20/2018 3. TBD 4. TBD 5. TBD |  | 1. 95% 2. 25% 3. 60% 4. 5% 5. 35% | 1. WIP 2. WIP 3. WIP 4. WIP 5. WIP
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000127878 | JHAS Valuation System Transformation | VST | PV | Anirban Naha | 1. Development for the addition of net premium fund in PALLM | 1.Q2 2018 |  | 1. 30% | 1. WIP | 1. GREEN
1200377 | John Hancock Life Insurance Company- USA | USI | 1000152166 | JH USI App Dev Flex Misc | Microfocus Azure Migration | PV | Anirban Naha | 1. Testing of email steps for RLTF and FRLT 2. Using Team City to promote bind files for CARE to the lower regions of Azure Server 3.Testing of the retrofitted components for FRLT and RLTF application for April changes 4.Run a full batch cycle for both RLTF and FRLT application in MOD region 5.Testing of print steps for RLTF and FRLT | 1. 4/27/2018 2. 4/30/2018 3. 5/10/2018 4.TBD 5. 5/4/2018 | 1.4/25/2018 | 1. 100% 3.10% | 1.Done 2.Not Started 3.WIP 4. Not Started 5. Not Started | 1.GREEN 3.GREEN

## ProjFinancial
[8 empty] | Project Revenue (USD) |  |  | Project CP%
Customer ID | Customer Name | LoB | ESA ID | ESA Name | Project Name (This column may not be applicable for thist tab) | Service Line | PM / POC Name | Bid Revenue | Last month Revenue | YTD Revenue | Bid CP% | Last Month CP% | YTD CP% | CP Improvement Plan | Remarks
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | NA | PV | Anirban Naha/Maheswari Manickam | 5071608.95 | 109112 | 109112 | NA | 53.2% | 53.2%
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000127878 | JHAS Valuation System Transformation | Na | PV | Anirban Naha | 2040881.61 | 32308 | 32308 | NA | 40.8% | 40.8%

## Healthcheck Metrics
[8 empty] | PAQ Ratio | Revenue per FTE | CP per FTE | Timesheet Compliance | Utilization | ON:OFF Ratio | Attrition% | Retention of Top Performers | Audit Findings
Customer ID | Customer Name | LoB | ESA ID | ESA Name | Project Name | Service Line | PM / POC Name
NOT TO BE WORKED UPON NOW

## Risks
Customer ID | Customer Name | LoB | ESA ID | ESA Name | Project Name | Service Line | PM / POC Name | Risks | Probability (0 - 1) | Impact (1 to 10) 10 -High | Risk Score | Mitigation Plan | Remarks
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | AEM | PV | Anirban Naha/ Maheswari Manickam | High Attrition rate of AEM resources | 1 | 9 | 9 | Checking with AEM lead(Maheswari) to have PAT ready with AEM training for backfill
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | WMD | PV | Anirban Naha/ Samiran Das | NA |  |  | 0 |  | Final Implementation is approaching. Developmnet is done.
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000127878 | JHAS Valuation System Transformation | VST | PV | Anirban Naha | NA |  |  | 0
1200377 | John Hancock Life Insurance Company- USA | USI | 1000152166 | JH USI App Dev Flex Misc | Microfocus Azure Migration | PV | Anirban Naha | 1.Micro Focus SORT Issue in the new Environment. | 1 | 1 | 1 | Microfocus team is working on this. | As alternate solution is available, no such impacts.

## Issues
Customer ID | Customer Name | LoB | ESA ID | ESA Name | Project Name | Service Line | PM / POC Name | Issues | Impact | Owner | Cognizant POC | Issue Reported By | Issue Reported On | Open Since (days) | Remarks
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | AEM | PV | Anirban Naha/ Maheswari Manickam | NA
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000140277 | JH SAS Web & Team Site Support | WMD | PV | Anirban Naha/ Samiran Das | NA
1200377 | John Hancock Life Insurance Company- USA | JHSS | 1000127878 | JHAS Valuation System Transformation | VST | PV | Anirban Naha | NA
1200377 | John Hancock Life Insurance Company- USA | USI | 1000152166 | JH USI App Dev Flex Misc | Microfocus Azure Migration | PV | Anirban Naha | The delivery was not affected for the SORT issue as Micro focus provided with a temporary fix. Micro focus team is working on this to provide a patch that will resolve the issue. | Jobs where sort utility is not supporting input files of different record lenght | Dev Team | Indranil Dutta | Anuva Pradhan (Dev)